## Slide 1: Transit Systems Planning
Module 3, Lesson 4

## Slide 2: Learning Objectives
Define systems planning
Understand the steps required for plan selection and the key features and elements required

## Slide 3: Overall Context
Systems planning requires a long-term approach that integrates with community goals and objectives and coordinates with other mode, land use and financial plans.

## Slide 4: What is Systems Planning?
Capital, operations and policy elements
Longer term focus 10-25+ years
Five to 10 year update cycle
Integrates with community goals and objectives
Coordinates with other mode plans
Coordinates with land use plan
Includes financial plan
Systems Planning
Service planning
Policy planning
Short range planning
Long-range planning
Capital planning
Strategic planning
Operations planning
Financial planning
Notes: Systems planning requires a long-term approach that integrates with community goals and objectives and coordinates with other mode, land use and financial plans.

## Slide 5: What is Systems Planning?
Highly dependent on the nature and goals for public transit in the target community.
Can be very significant initiative in communities where transit plays a meaningful role in providing transportation capacity and/or in shaping urban development.
Can be more significant in growing communities where transit is looked at as a critical means of meeting future mobility needs.
Occasionally produces a system master plan that is part of a regional commitment to a guideway network (MARTA, WMATA, BART, DART, etc), and can be a centerpiece in a local referendum or major decision.

## Slide 6: Sample System Plan
Adopted Regional System, 1968
After extensive discussions with local planning bodies, the WMATA planners settled on a 97.2 mile system (44.8 miles in subway), with 88 stations and “future extensions” mapped in every direction. In February 1968, they named it Metro., WMATA.

## Slide 8: Systems Planning Steps
Goals and Objectives
Development of alternative plans
Specification of the evaluation criteria
Forecasts of future conditions
Stakeholder input
Assessment of current conditions
Evaluation of alternative plans
Corridor or project planning
Plan refinement
Plan selection

## Slide 9: Systems Planning: Key Features for Large Urban Area Systems Plans
Carried out in collaboration with other modes and with the land-use planning entity.
Often major multiyear initiative.
Typically involves major transportation or transportation and land-use modeling efforts.
Followed by corridor or project development planning.

## Slide 10: Stakeholders
Existing and future passengers
Local citizens/taxpayers
Vested interest groups in all relevant areas associated with project impacts (energy, air-quality, environment, mobility, population segments [seniors, disabled, minority, etc.], business, etc.).
Regional, state, federal authorities who might be involved in providing approvals and funding.

## Slide 11: Transit Plan Development Evaluation, and Selection
Adopted from Vuchic
Local conditions
  Topography
  Roadway network
  Land-use
  Financial capacity
  Environmental considerations
Transit system goals and objectives: role of transit
Travel demand (current and forecast)
Origin destination pattern
Flow volumes
level of service goals
Design alternative plans
Mode or modes
Network configuration/alignments
Network extent
Carpooling/vanpool
Bus
Express bus
Streetcar
Bus rapid transit
Light rail
Heavy rail
Commuter rail
other
Evaluation and selection of plan
Matching modes to market characteristics

## Slide 12: Guidance in Matching Technologies to Market Characteristics

## Slide 13: Steps in Project Planning and Development

## Slide 14: New Starts Planning and Project Development Process
Alternatives Analysis
Final Design
Commitment of Non-Federal Funding,
Construction Plans, ROW Acquisition,
Before-After Data Collection Plan,
FTA Evaluation for FFGA,
Begin Negotiations
Project Management Oversight
Construction
Preliminary Engineering
Complete NEPA Process
Refinement of Financial Plan
Select LPA,
MPO Action,Develop Criteria,
PMP
FTA Decision
On Entry
into PE
FTA Decision
On Entry
into Final Design
Full Funding
Grant Agreement
Preliminary Engineering
Final Design
Construction
Decision Point
Major Development
Stage
Systems Planning
Planning
Decisions
Needs
Policies
Priority corridor(s)
Decisions
Mode, general alignment
Financial plan
Adopt LPA into LRTP
Decisions
Refinements to LPA
Final scope and cost
Complete NEPA
Implement financial plan
Refine Project Management Plan
Enhance Technical Capacity

## Slide 15: Small Starts Planning and Project Development
Alternatives Analysis
Project Development
Select LPA
FTA Approval
to Start PD
Project Construction
Grant Agreement
System Planning
Decisions
Mode, general alignment
Financial plan
Decisions
Needs
Policies
Priority corridor(s)
Decisions
Refinements to LPA
Final scope and cost
Complete NEPA
Implement financial plan

## Slide 16: Key Decisions for Each Phase of New Starts Project Development
Systems planning: priority corridor
Alternatives analysis: mode and alignment
Preliminary engineering: final scope/cost, completion of NEPA, financial plan
Final design: construction documents
Full Funding Grant Agreement
  FTA: funding
  Project sponsor: delivery of the project

## Slide 17: Operating Facilities Element
Operating facilities or garages
  Approximately 1 per 200 vehicles.
  Geographically spaced to minimize deadhead time.
  Located to minimize neighborhood impact and optimize access to transit network.
Occasionally separated by mode and functions (storage and light maintenance, heavy maintenance).

## Slide 18: Passenger Facilities Element
Transit centers – enable transferring between vehicles and provide operator layover points. Can be attractive community assets.
Park-and-ride lots – support express services.
Passenger shelters and facilities – provide comfort, service awareness, and passenger support information.

## Slide 19: Fleet Element
Match capacity needs to size and types of transit vehicles.
Establish a program of vehicle replacement to:
  ensure adequate capacity,
  enhance labor productivity
  balance capital spending requirements,
  support a stable maintenance workload,
  ensure compatibility with fueling, communications, maintenance, cleaning, and related system elements.

## Slide 20: References
Vukan Vuchic, Urban Transit Operations, Planning and Economics, John Wiley and Sons, Inc. 2005, Part III, Transit Systems Planning and Mode Selection, pp. 469-612.
George Gray and Lester Hoel, Editors, Public Transportation, Chapter 13, System and Service Planning, Herbert Levinson, pp 369-406